## Event Timeline
Milestone | Task | Owner | Start Date | Due Date | Status | Notes
120 DAYS OUT
| Book venue and sign contract | Event Lead |  |  | Not Started | Get signed before deposit deadline
| Set event budget | Finance |  |  | Not Started | Include 10% contingency
| Select event tech platforms (Cvent, Award Force, etc.) | Operations |  |  | Not Started
| Draft master event timeline | Event Lead |  |  | Not Started | This document
90 DAYS OUT
| Open registration in Cvent | Operations |  |  | Not Started | Test all reg types first
| Launch call for submissions/entries | Operations |  |  | Not Started | Award Force setup must be complete
| Begin speaker/judge recruitment | Event Lead |  |  | Not Started
| Send save-the-date communications | Marketing |  |  | Not Started
60 DAYS OUT
| Finalize hotel event orders (BEOs) | Operations |  |  | Not Started | Cross-check with run of show
| Confirm AV requirements per room | AV/Tech |  |  | Not Started | Don't wait on this
| Close submissions/entries | Operations |  |  | Not Started
| Begin judging setup in Award Force | Operations |  |  | Not Started
30 DAYS OUT
| Finalize staffing plan | Event Lead |  |  | Not Started | Cross-reference with ROS
| Design and order printed materials | Marketing |  |  | Not Started | Badges, programs, signage
| Send detailed logistics email to all attendees | Operations |  |  | Not Started
| Complete judging and notify results | Operations |  |  | Not Started
14 DAYS OUT
| Final venue walkthrough | Event Lead |  |  | Not Started | Check every room setup
| Reconcile data across all platforms | Operations |  |  | Not Started | AF ↔ Cvent ↔ Spreadsheet
| Confirm catering guarantees | Operations |  |  | Not Started | Usually due 72 hrs before
| Brief all staff and volunteers | Event Lead |  |  | Not Started
7 DAYS OUT
| Print and assemble all materials | Operations |  |  | Not Started | QA check badge data!
| Send final reminder email | Operations |  |  | Not Started | Include parking, dress code, schedule
| Test all AV in every room | AV/Tech |  |  | Not Started
1 DAY OUT
| Deliver materials to venue | Operations |  |  | Not Started
| Final room setup walk | Event Lead |  |  | Not Started
| Charge all devices, print run sheets | All Staff |  |  | Not Started | Print 2 copies of everything
POST-EVENT
| Send thank you + survey email | Operations |  |  | Not Started | Within 24 hours
| Export all data from all platforms | Operations |  |  | Not Started | Before season closes!
| Conduct team debrief | Event Lead |  |  | Not Started | What worked, what didn't, what to change
| Archive all documents | Operations |  |  | Not Started | Organized folder structure
| Update template for next year | Event Lead |  |  | Not Started | Do it while memory is fresh

## Status Key
Status Options
Not Started
In Progress
Blocked
Complete
Cancelled